## Checklist
Onboarding checklist: preboarding to day 90
New hire | <name>
Role | <job title>
Start date | <date>
Owner of the checklist | <name, e.g. office manager or HR>
Manager | <name>
Buddy | <name>
Phase | Task | Role | Person responsible | Due | Status | Notes
0 Preboarding | File the contract, open the personnel file, request documents (tax ID, social security number, health insurance, bank details) | HR |  |  | open
0 Preboarding | Notify IT and the manager in writing of start date, role and required systems - at least three weeks before day one | HR |  |  | open
0 Preboarding | Welcome email two weeks before the start: who meets the person when and where, what to bring, what day one looks like | HR |  |  | open
0 Preboarding | Order or reserve the device; create user account, email and calendar; request access to specialist applications | IT |  |  | open
0 Preboarding | Store the credentials so the manager can hand them over on day one | IT |  |  | open
0 Preboarding | Arrange workspace, keys, parking; name a buddy; write down a plan for the first five days | Manager |  |  | open
0 Preboarding | Test the access yourself the day before the start | Manager |  |  | open
0 Preboarding | Short personal message before the start; block out lunch on day one | Buddy |  |  | open
1 Day one | Greet in person and on time - if a meeting collides, the meeting moves, not the welcome | Manager |  |  | open
1 Day one | Tour and team introductions, show responsibilities on a current org chart | Manager |  |  | open
1 Day one | Hand over the device, first login together, check printer and phone (goal: first email from own mailbox before noon) | IT |  |  | open
1 Day one | Formalities in one hour max: time tracking, vacation, sick leave, safety briefing, data protection, unwritten rules | HR |  |  | open
1 Day one | Lunch and the unofficial rules: who gets asked about what | Buddy |  |  | open
1 Day one | Short conversation at the end of the day: what is open, what is missing, what is on tomorrow | Manager |  |  | open
2 Week one | Expectations conversation: goals for 30, 60 and 90 days in writing, both keep a copy | Manager |  |  | open
2 Week one | Meetings with the role's interfaces, 20 minutes per area | Manager |  |  | open
2 Week one | Hand over the job training plan, first task with a result and a deadline | Manager |  |  | open
2 Week one | Follow-up on day 3: is an application missing? | IT |  |  | open
2 Week one | Invitations to team meetings, staff meeting and first-quarter training sessions | HR |  |  | open
2 Week one | Five minutes of checking in every day; show where documented processes live and how to search them | Buddy |  |  | open
3 Month one | Feedback conversation after 30 days (45 minutes): what goes well, what is missing, what surprised you | Manager |  |  | open
3 Month one | Compare against the job training plan: which processes are mastered, which not - and why | Manager |  |  | open
3 Month one | Ask about the organizational start; feed the answers back into this checklist | HR |  |  | open
3 Month one | Review permissions that were only meant for the training period | IT |  |  | open
3 Month one | Move from daily company to one fixed weekly slot | Buddy |  |  | open
4 Through day 90 | Conversation after 60 days, focused on independence | Manager |  |  | open
4 Through day 90 | Conversation after 90 days: status against week-one expectations, outcome in writing | Manager |  |  | open
4 Through day 90 | End of probation in the calendar four weeks ahead; close onboarding formally, briefings documented | HR |  |  | open
4 Through day 90 | End the buddy arrangement officially, stay in touch | Buddy |  |  | open
4 Through day 90 | Give the new person a role in the next onboarding | Manager |  |  | open
Full guide: https://wissa.ai/en/guides/onboarding-checklist
Template by wissa.ai - https://wissa.ai/en

## Metrics
Metric | Definition | How to collect it | Warning sign | Your value
Early turnover | Share of new hires who leave within the first 12 months | List all hires of the past two years, mark the departures | Above 20 percent, or several exits during probation with similar reasons
Time to productivity | Days from the start until the core tasks are handled independently | The manager's assessment in the 30, 60 and 90 day conversations | Clearly longer than for comparable roles, or swinging widely
Template by wissa.ai - https://wissa.ai/en